## Sheet1
Project Time Performance Tracking | [5 empty] | Format No. Rev. No. & Date. | : :
Year: ________________ Project Manager _____________________ Sign ___________
Project Name | Project Type | Estmiated Start | Estimated Finish | Estimated Days | Actual Start | Actual Finish | Actual Days | Variance (Days)
Project - A | Cost Reduction | 2015-01-04 | 2015-03-04 | 59 | 2015-01-10 | 2015-03-25 | 74 | 15
Project - B | Control Management | 2015-01-18 | 2015-02-21 | 34 | 2015-01-18 | 2015-02-28 | 41 | 7
Project - C | RM Planning | 2015-02-06 | 2015-04-16 | 69 | 2015-02-08 | 2015-04-30 | 81 | 12
Project - D | Purchase Planning | 2015-02-24 | 2015-04-25 | 60 | 2015-02-24 | 2015-05-12 | 77 | 17
Project - E | Re-Engineering | 2015-03-08 | 2015-03-18 | 10 | 2015-03-12 | 2015-03-25 | 13 | 3
Project - F | Process Improvement | 2015-03-19 | 2015-04-29 | 41 | 2015-03-22 | 2015-05-08 | 47 | 6
Project - G | New Plant Setup | 2015-04-10 | 2015-05-12 | 32 | 2015-04-13 | 2015-05-30 | 47 | 15
Project - H | Mfg. Modification | 2015-04-18 | 2015-06-22 | 65 | 2015-04-20 | 2015-07-05 | 76 | 11